## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US-1 | Set up the complete environment with JDK, IntelliJ, and GitHub integration. | MUST HAVE |  | Jandhyala Venkata Akhilesh | 3- Completed
Sprint 1 | Sprint 1 | US-2 | Design and implement the Product and InventoryManager classes using OOP principles and proper exception handling. | MUST HAVE | US-1 | Jandhyala Venkata Akhilesh | 3- Completed
Sprint 1 | Sprint 1 | US-3 | Configure data persistence using CSV files and manage version control through Git workflow. | MUST HAVE | US-2 | Jandhyala Venkata Akhilesh | 3- Completed
Sprint 1 | Sprint 1 | US-4 | Practice SQL queries and establish a JDBC connection between the database and Java project. | MUST HAVE |  | Jandhyala Venkata Akhilesh | 3- Completed
Sprint 2 | Sprint 2 | US-5 | Develop methods for fetching records from the database (getAllProducts, getProductById) and integrate them into the console menu. | MUST HAVE | US-4 | Jandhyala Venkata Akhilesh | 3- Completed
Sprint 2 | Sprint 2 | US-6 | Implement functionality for updating and deleting product details through database operations. | MUST HAVE | US-4 | Jandhyala Venkata Akhilesh | 3- Completed
Sprint 2 | Sprint 2 | US-7 | Combine all CRUD operations into a single end-to-end console-based test flow. | MUST HAVE | US - 5,6 | Jandhyala Venkata Akhilesh | 3- Completed
Sprint 2 | Sprint 2 | US-8 | Apply robust input validation and structured error-handling mechanisms throughout the application. | MUST HAVE | US-7 | Jandhyala Venkata Akhilesh | 3- Completed
Sprint 2 | Sprint 2 | US-9 | Perform JUnit testing to verify functionality and ensure code reliability. | MUST HAVE | US-7 | Jandhyala Venkata Akhilesh | 3- Completed
Sprint 3 | Sprint 3 | US-10 | Build a CSVHelper class to handle exporting of product inventory data into CSV format. | MUST HAVE | US-3 | Jandhyala Venkata Akhilesh | 3- Completed
Sprint 3 | Sprint 3 | US-11 | Integrate email-sending functionality using SMTP to deliver reports. | MUST HAVE | US-10 | Jandhyala Venkata Akhilesh | 3- Completed
Sprint 3 | Sprint 3 | US-12 | Create an admin panel option to generate detailed inventory reports. | SHOULD HAVE | US-10,11 | Jandhyala Venkata Akhilesh | 3- Completed
Sprint 3 | Sprint 3 | US-13 | Connect database, CSV, and email modules to enable reporting. | MUST HAVE | US-12 | Jandhyala Venkata Akhilesh | 3- Completed
Sprint 3 | Sprint 3 | US-14 | Implement OTP-based user verification during registration to improve security. | SHOULD HAVE | US-13 | Jandhyala Venkata Akhilesh | 3- Completed
Sprint 3 | Sprint 3 | US-15 | Add “Verify Email” and “Resend OTP” features in the admin or main menu. | COULD HAVE | US-14 | Jandhyala Venkata Akhilesh | 3- Completed
Sprint 4 | Sprint 4 | US-16 | Develop a monitoring module that alerts admin for low stock using threshold logic. | MUST HAVE |  | Jandhyala Venkata Akhilesh | 3- Completed
Sprint 4 | Sprint 4 | US-17 | Automate report generation and alert scheduling using background tasks. | MUST HAVE | US-16 | Jandhyala Venkata Akhilesh | 3- Completed
Sprint 4 | Sprint 4 | US-18 | Integrate email notification system for low-stock products in real-time. | MUST HAVE | US-16 | Jandhyala Venkata Akhilesh | 3- Completed
Sprint 4 | Sprint 4 | US-19 | Package and deploy the entire inventory management system. | MUST HAVE |  | Jandhyala Venkata Akhilesh | 3- Completed
Note on F1: ====== ID#AAABqnR-1bo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.